## RTM
Requirement ID | Requirement Description | Requirement Type | Priority | Module | Test Case ID | Test Case Description | Test Execution Status | Defect ID | Requirement Status | Remarks
R-101 | User is able to search on basis of partial keywords eg new mug should show result for mug | Functional | High | Search | TC-001 | Validating User is able to search on basis of partial keywords eg new mug should show result for mug | Fail | D-001 | Implemented | Not working correctly
R-102 | Password must be 8+ characters | Non-Functional | Medium | Login | TC-002 | Verify password length check | Fail | D-005 | In Progress | Validation issue
R-103 | User can reset password | Functional | High | Login | TC-003 | Verify password reset email flow | Not Executed | - | Pending | To be tested
R-104 | Dashboard should load in 3s | Performance | Low | Dashboard | TC-004 | Measure dashboard load time | Pass | - | Implemented | Performance OK

## TestCase
Project Name: | Airbnb
Module Name: | Search Bar
Created By: | Priyanka Arora
Date of Creation: | 2025-03-03
Date of Review:
Test Case Id | Requirement Id | Test Case Scenario | Test Case Description | Precondition | Test case steps Taken | Test Data | Expected Result | Actual Result | Status | Defect Id
TC_01 | R-101 | Validating cancel icon on check in date at home screen main search bar | When user tries to cancel checkin date after selecting the checkin date. Checkin date should reset. | 1. User is on home page 2. User has already selected checkin and checkout date | 1. User select check in date 2. User selects check out date 3. User cancels check in date | checkinDate=20th april 2024 checkoutDate=24th april 2024 | After clicking cancel icon, checkin date gets reset | As Expected | Passed
TC_02 | R-102 | Validating dropdown values getting selected on top right search bar at home screen | Drodown suggestions on the search bar located at top right of the screen should be selectable on single click | 1. User is on home page | 1. Click on the search bar 2. Select dropdown value on single click | DropdownValue=Data Structures | The dropdown value should get selected on single click | The dropdown value did not get selected on single click | Failed | Defect_Id_01
TC_03 | R-103 | Validating the search module of property review section for translated keyword | When user translates the site and then go to property review and uses search with a translated keyword. Search filter should work. | 1. User is on home page 2. User has translated the site | 1. Enter location 2. Enter date 3. Emter number of people 4. Go to search 5. Enter translated keyword | location=kasol date= 17-18 july2024 guests=2 tranlated language=Hindi search keyword=प्रॉपर्टी | Search filter works for the translated keyword in the review section | Search filter is not working after translating the website on review section | Failed | Defect_Id_02
TC_04 | R-104 | Validating property_type filter is working when applied first and searched for the location later | When user tries to use property_type filter first on the main search and then selects location, date, guests. Property_type filter should be applied on the search results. | 1. User on home page | 1. Property type is selected 2. Location is selected 3. Date ie selected. 4. Guests selected | property_type=camping location=kasol date= 17-18 july2024 guests=2 |  |  | Not Executed