## RTM
Requirement ID | Requirement Description | Requirement Type | Priority | Module | Test Case ID | Test Case Description | Test Execution Status | Defect ID | Requirement Status | Remarks
R-101 | User should be able to log in | Functional | High | Login | TC-001 | Verify login with valid inputs | Pass | - | Implemented | Working fine
R-102 | Password must be 8+ characters | Non-Functional | Medium | Login | TC-002 | Verify password length check | Fail | D-005 | In Progress | Validation issue
R-103 | User can reset password | Functional | High | Login | TC-003 | Verify password reset email flow | Not Executed | - | Pending | To be tested
R-104 | Dashboard should load in 3s | Performance | Low | Dashboard | TC-004 | Measure dashboard load time | Pass | - | Implemented | Performance OK

## TestExecutionReport
Requirement ID | Requirement Description | Module | Test Case ID | Executed By | Execution Date | Execution Status | Defect ID | Comments
R-101 | Search should work on partial key inputs like "new mug" | Search Module | TC-001,TC-006,TC-007,TC-008 | Tester A | 2025-09-25 | Pass,Pass,Fail,Fail,Fail | - | Working partially
|  | Login | TC-002 | Tester B | 2025-09-25 | Fail | D-005 | Validation issue
|  | Login | TC-003 | Tester A | 2025-09-26 | Not Executed | - | Pending execution
|  | Dashboard | TC-004 | Tester C | 2025-09-26 | Pass | - | Performance acceptable
|  | Login | TC-005 | Tester B | 2025-09-27 | Pass | - | Logout working fine

## Test Case Review
Created Date | Updated Date | Reviewer Name | Test Case ID | Feedback | Tester | Comments | Status
2025-09-26 | 2025-09-26 | Priyanka (Senior QA) | TC-001,TC-002 | It is mandatory to provide precondition and assumption don’t skip it | Rajat | Noted. And Fixed | Closed
2025-09-26 | 2025-09-26 | Priyanka (Senior QA) | TC-009,TC-010 | Test Data is incomplete. Do specify browser used | Rajat | Noted. Added | Closed